## Sheet1
S. No. | Difficulty | Assigned To | Status | Description
1 | Easy | Divya | Done | project has been renamed to CodeArea its previous name was UIDesigner, make sure name UIDesigner is not used in this project any more.
2 | Easy # | Divya | Obsolete | Solution is constantly watching for A json file change in whole folder, restrict it to watch A particular file.
3 | Easy | Divya | Done | Rename doSomething
4 | Medium | Akanksha | Done | make the input box movable, i.e it should be able to be dragged around.
5 | Hard | Yeshwanth | Done | convert Draw area elements to objects and use project DrawAreatoJSON to convert to json file
6 | Hard | Rishabh | In progress | Restructure Solution to follow MVVM Architecture
7 | Easy | Divya | Obsolete | Clear unused reference in project Draw area
8 | Medium | Rishabh and Shridhar |  | Tweaking formulae
9 | Medium | Rishabh and Shridhar |  | Move event from window to grid
9 | Medium | Divya |  | Add controls to ToolBox
10 | Medium | Rishabh |  | Add properties panel
11 | Easy | Smriti |  | Set Unique names to blocks
12 | Medium # | Smriti |  | Get DB connectivity to pull field's properties